|  | MASTER WORK ORDER Alder Residence — Portland, OR |
| --- | --- |

| Customer | Casey Alder |
| --- | --- |
| Address | 1234 SE Alder St, Portland, OR 97215 |
| Homeowner phone | (503) 555-0136 |
| Questions on site | Kyle Kanooth, Project Manager — (503) 555-0117 |
| Job # | 2026-0714 |
| Install Dates | Aug 4–5, QC day Aug 6 |
| Crew Lead | ___________________________ |

⚠  SAFETY FLAGS: LEAD PAINT — 1962 home. Use lead-safe (RRP) practices any time you disturb paint.

Site Access & Homeowner Notes

•  Access: front door. Lockbox on the hose bib — code comes from the homeowner. Park in the driveway and keep the sidewalk clear.

•  Occupants: Casey works from home in the back office. The cat is indoors-only — keep exterior doors closed.

The House

•  1962 one-story bungalow, 940 sf. Vented attic, crawlspace foundation.

•  Existing heat is a gas furnace in the hall closet with ducts through the attic. It comes out Day 1.

•  The gas meter stays live for the range and water heater. Cap the gas at the furnace only.

Homeowner Concerns (from walkthrough)

•  Comfort first. The living room runs cold every winter and the bedroom overheats in summer. The two heads are placed to fix exactly that.

•  The kitchen has no exhaust at all. The new hood is a big deal to Casey — make it right.

•  The kitchen remodel is NOT in this scope (homeowner aware). The hood vents through the existing cabinet run.

Trades Summary

| Trade | In this job |
| --- | --- |
| HVAC | Remove the gas furnace · Install the ductless heat pump · Range hood duct · Bath fan |
| WEATHERIZATION | Attic air seal · Attic prep + insulation |
| ELECTRICAL | New 240V circuit for the heat pump |

Schedule

| Day | Crews | Work |
| --- | --- | --- |
| Day 1 (Mon) — Furnace out + attic open + air-seal start | HVAC · WX · ELEC | HVAC: pull the furnace, cap the gas at the appliance, take the attic ducts out · WX: vacuum the attic clean, start the air seal, hold the hood and bath-fan duct spots open · ELEC: run the ODU circuit and turn it on |
| Day 2 (Tue) — Heat pump + ducts + seal + blow | HVAC · WX | HVAC: set the ODU, both heads, and linesets, run the hood and bath-fan ducts, commission both zones · WX: seal around the new ducts, finish the air seal, finish attic prep · blower door proves the plane tight · WX: blow R-49 |
| QC Day (Wed) — Test + walkthrough + sign-off | Lead + assessor | Final blower door · walk every measure against this work order · Casey signs off |

•  The attic opens Day 1. Every duct runs Day 2 through the spots WX held open. Nothing gets sealed over or blown until the ducts are in.

•  One rule decides Day 2's order: air-seal, blower door, then blow. Cellulose over a leaky plane is buried rework — the blower door proves the plane tight before the machine starts.

•  Both install crews share the site Days 1–2. The whole install finishes Day 2.

•  The QC day is not a production day. Final numbers, full walkthrough, sign-off.

•  If the Day-2 blower door fails, chase leaks and retest before blowing. If that pushes past end of day, call Kyle before changing the rest of the week.

Book these dates:

Day 1 (Mon) · Furnace out + attic open + air-seal start:  _______________________

Day 2 (Tue) · Heat pump + ducts + seal + blow:  _______________________

QC Day (Wed) · Test + walkthrough + sign-off:  _______________________

Key Gates — sign off before moving on

☐  Day 1: attic vacuumed and open · furnace out, gas capped at the appliance · ODU circuit live    ______  (crew lead / time)

☐  Day 2: air seal complete · blower door result: __________ CFM50 (a pass starts the blow) · R-49 blown, depth markers visible    ______  (crew lead / time)

☐  QC Day: every measure walked · Casey signed off · final photos sent to the office    ______  (crew lead / time)

Scope of Work

| Trade | Task | Details | Location |
| --- | --- | --- | --- |
| HVAC | Remove the gas furnace | Cap the gas at the appliance. Remove the furnace and all attic duct runs. Haul away. | Hall closet + attic |
| HVAC | Install the ductless heat pump | 24k cold-climate outdoor unit on the east-wall pad. 12k wall head in the living room, 9k in the bedroom. Linesets run through the attic. | East wall, living room, bedroom |
| HVAC | Range hood duct | Duct the new 300 CFM hood through the upper cabinet and out the wall cap with a damper. | Kitchen |
| HVAC | Bath fan | ENERGY STAR 110 CFM fan with humidistat. Duct out the roof — first 3 feet straight. | Hall bath |
| WEATHERIZATION | Attic air seal | The full ceiling plane: top plates, can lights, penetrations, flue dam. Hold the hood and bath-fan duct spots open Day 1. Seal around the new ducts after HVAC runs them Day 2. | Attic |
| WEATHERIZATION | Attic prep + insulation | Baffles at every eave bay. Hatch dam + weatherstrip. 3 depth markers. Then blow R-49 cellulose over 940 sf. | Attic |
| ELECTRICAL | New 240V circuit for the heat pump | 25A 2-pole breaker, 10/2 from the panel to the east-wall disconnect, whip to the ODU. | Panel (garage) to east wall |

Equipment Arriving

| Item | Model | Qty |
| --- | --- | --- |
| Outdoor unit | 24k cold-climate ductless ODU | 1 |
| Wall heads | 12k (living) + 9k (bedroom) | 2 |
| Bath fan | 110 CFM ENERGY STAR, humidistat | 1 |
| Range hood | 300 CFM ducted | 1 |
| Disconnect + whip | 60A non-fused | 1 |

DAY 1 (MON) — FURNACE OUT + ATTIC OPEN + AIR-SEAL START — HVAC · WX · ELEC

☐  HVAC — pull the furnace, cap the gas at the appliance, take the attic ducts out

☐  WX — vacuum the attic clean, start the air seal, hold the hood and bath-fan duct spots open

☐  ELEC — run the ODU circuit and turn it on

☐  DAY 1 (MON) — FURNACE OUT + ATTIC OPEN + AIR-SEAL START DONE — site clean and safe, next phase ready

☐  Photos of today's work sent to the office

DAY 2 (TUE) — HEAT PUMP + DUCTS + SEAL + BLOW — HVAC · WX

☐  HVAC — set the ODU, both heads, and linesets, run the hood and bath-fan ducts, commission both zones

☐  WX — seal around the new ducts, finish the air seal, finish attic prep

☐  blower door proves the plane tight

☐  WX — blow R-49

☐  DAY 2 (TUE) — HEAT PUMP + DUCTS + SEAL + BLOW DONE — site clean and safe, next phase ready

☐  Photos of today's work sent to the office

QC DAY (WED) — TEST + WALKTHROUGH + SIGN-OFF — LEAD + ASSESSOR

☐  Final blower door

☐  walk every measure against this work order

☐  Casey signs off

☐  QC DAY (WED) — TEST + WALKTHROUGH + SIGN-OFF DONE — site clean and safe, next phase ready

☐  Photos of today's work sent to the office

Notes for Crew

•  Casey is on video calls in the back office. Knock at the front door. Headphones mean go around.

•  The cat is friendly and sneaky. Check for her before closing the attic hatch.

•  hvac: The hood and bath-fan duct spots are marked with orange paint in the attic — WX held them open Day 1. Run your ducts there, then tell WX so they can seal around them.

•  elec: The panel is in the garage, two spare spaces lower right. Land the circuit there and label it HEAT PUMP.

•  wx: Depth markers go in before the blow — minimum 3, visible from the hatch.

Homeowner Walkthrough

☐  Both remotes: heat and cool on each head. Set "heat" or "cool" — leave "auto" alone. Fan on automatic.

☐  Filter cleaning on both heads. Demonstrate the first one hands-on; Casey does the second.

☐  Bath fan humidistat: what the light means and when it runs on its own.

☐  Range hood damper cap outside — show what it looks like when it's working.

☐  The new breaker in the panel, labeled HEAT PUMP.

☐  Manuals and remotes stay on the kitchen counter.

Reference Photos

| Furnace closet in the hallway. Cap the gas at the appliance — the meter stays live for the range and water heater. | Attic from the hatch. Vacuum out, air-seal, baffles at every eave bay — all before the blow. |
| --- | --- |
| Panel in the garage. Land the ONE new 25A/240V heat-pump circuit in the spare spaces, lower right. Label it HEAT PUMP. | East wall. The ODU pad goes here. Seal the lineset penetration after the ducts run. |
| Hall bath fan location. Duct out the roof — first 3 feet straight. | Range wall. The hood ducts through the upper cabinet and out the wall cap. Mount the controls where Casey can reach them. |

Completion Sign-Off

| Crew Lead | Signature: ______________________________ Date: ____________ |
| --- | --- |
| Homeowner | Signature: ______________________________ Date: ____________ |
| Final QC by | Name: ____________________ Blower door / results attached ☐ |

Resilient Retrofits  ·  CCB# 245539  ·  Prepared by: Kyle Kanooth